## Overview
AAI-501 Final Team Project - Project Planner
Owner | Michael Valderrama (AAI-501 Group 7)
Created | 2026-06-30
Purpose | One command center to make sense of the problem and methods, plan how the dataset gets manipulated, and keep every piece lined up to the 280-pt rubric.
Problem statement | [Fill once topic is chosen: what real-world / business problem are we solving, and on what dataset?]
Dataset | [Name + source link + #rows + #features once chosen. Must be >=1000 rows, public or self-provided, light preprocessing.]
Algorithms (need >=2 types) | [e.g., Classification + Clustering, or two classifiers compared - filled from Methods Pick tab.]
Mode | SOLO project - approved by AVB 2026-06-30. All work owned by Michael.
How to use | 1) Pick topic+dataset. 2) Define lanes on 'Question x Method Grid'. 3) Log variables on 'Data Dictionary'. 4) Choose algorithms on 'Methods Pick'. 5) Track gates on 'Milestones'. 6) Keep 'Rubric Tracker' green.
Legend | Green cell = done. Yellow cell = needs attention / decision.

## Question x Method Grid
Question x Method Grid - each column is an analysis lane (a question/comparison); each row is a planning lens
Problem statement: [one-sentence framing of the analysis goal once topic is chosen]
Attribute \ Lane | Lane 1 (e.g., RQ1) | Lane 2 (e.g., RQ2) | Lane 3 (e.g., ML-Q model A) | Lane 4 (comparison) | Lane 5 (stretch)
Narrative | Plain-English story of what this lane is and why it earns its place.
Question (What) | The specific question this lane answers.
Why it matters | Why it's needed; how it ties to the problem/business value.
Type | inference / prediction / clustering / bridge.
Algorithm / Method | Which algorithm(s) - must roll up to >=2 types across lanes.
Features / variables | Which columns feed this lane.
Data prep / manipulation | Cleaning, encoding, scaling, feature selection needed here.
Experimental comparison | What is compared (algorithms / tuning / simpler model).
Expected output / metric | What result + metric (AUC, F1, silhouette, RMSE...).
Rubric tie-in | Which rubric bucket(s) this earns.
Status | Green when done.

## Rubric Tracker
Rubric Tracker - Assignment 7.2 Final Team Project (280 pts)
Criterion | Weight | Points | What 'Meets/Exceeds' looks like | Where it's earned | Status
Project Selection & Setup | 15% | 42 | Clear objectives, feasible approach, dataset available, properly scoped | Topic lock + proposal + Overview
Algorithm Descriptions, Theory & Source Code | 25% | 70 | Clear algorithm description, explicit theory w/ proper math/logic, self-documenting code | Question grid + Methods Pick + report
Execution & Output | 25% | 70 | Code runs on the data; complete results from multiple runs | Modeling phase + notebook
Analysis, Results & Conclusions | 20% | 56 | Well-presented results, accurate conclusions, successful project | Comparison + report results
Report Format, Citations, Content | 15% | 42 | Proper length, properly cited (APA 7), professional | Report + references from proposal
Total |  | 280
Separate items: Peer Evaluation 7.3 = 45 pts (each member submits). Proposal 3.3 = 5 pts, Status 4.3 = 5 pts.

## Milestones
Milestones - hard dates are Mondays 11:59pm PT. No extensions.
Milestone | Window | Hard due | Deliverable / gate | Owner | Status
M0 Kickoff & setup | Jun 30 - Jul 2 | - | Repo live, channel set, roles, team/solo confirmed | Me
M1 Topic & dataset lock | Jul 3 - Jul 6 | - | Dataset downloaded, passes fit-check | Me
M2 Proposal (3.3) | Jul 7 - Jul 13 | Jul 13 | 1-2 pp proposal + APA refs (5 pts) | Me
M3 Data + baseline + Status (4.3) | Jul 14 - Jul 20 | Jul 20 | Clean data, EDA, 1 baseline, status form (5 pts) | Me
M4 Modeling & experiments | Jul 21 - Aug 3 | - | 2+ algorithms compared, figures | Me
M5 Report+code+slides+video (7.2) | Aug 4 - Aug 10 | Aug 10 | Report, repo, deck, video link (280 pts) | Me
M6 Peer evaluation (7.3) | Aug 8 - Aug 10 | Aug 10 | Each member submits (45 pts) | Me

## Data Dictionary
Data Dictionary - fill once the dataset is chosen; track every manipulation
Variable | Type | Description | Role (feature/target/ID) | Transformation / manipulation | Notes

## Methods Pick
Methods Pick - choose >=2 different algorithm TYPES with an experimental comparison
Candidate method | Algorithm type | Why it fits our data | Pros | Cons | Selected?
Logistic Regression | Classification (linear) | Interpretable baseline for binary/multiclass | Coefficients, fast, explainable | Linear boundaries only
Random Forest | Classification (tree ensemble) | Non-linear, gives feature importance | Strong, importance, robust | Less interpretable
XGBoost / Gradient Boosting | Classification/Regression (boosting) | High accuracy on tabular | Top tabular performance | Tuning, overfit risk
K-Means | Clustering | Find lifestyle/segment groups | Simple, fast | Pick k, spherical assumption
PCA | Dimensionality reduction | Reduce many features, visualize | Denoise, 2D plots | Components less interpretable
Linear Regression | Regression | Predict a continuous target | Simple, interpretable | Linearity assumptions
KNN | Classification/Regression | Simple non-parametric comparator | No training, intuitive | Slow at scale, scaling-sensitive